## Sheet1
Task | Start Date | End Date | June | [10 empty] | July | [30 empty] | August
|  |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Analysis | 2022-06-20 | 2022-06-30 | bar: June 20 to June 30
Project Initiation | 2022-06-20 | 2022-06-30 | bar: June 20 to June 30
Thinking Abstractly | 2022-06-29 | 2022-06-30 | bar: June 29 to June 30
Decomposition | 2022-06-28 | 2022-06-29 | bar: June 28 to June 29
Thinking ahead | 2022-06-29 | 2022-06-30 | bar: June 29 to June 30
Thinking concurrently | 2022-06-29 | 2022-06-30 | bar: June 29 to June 30
Plan - Gantt chart | 2022-06-29 | 2022-06-30 | bar: June 30
Analysis complete | 2022-06-29 | 2022-06-30 | bar: June 30
Sprint 1 (Iteration 1) | 2022-07-01 | 2022-07-30 | bar: July 1 to July 30
Sprint analysis | bar: July 1 to July 5
Technical design | bar: July 6 to July 10
Development | bar: July 11 to July 23
Testing | bar: July 23 to July 30
Sprint 1 complete | bar: July 30
Sprint 2 (Iteration 2) | 2022-08-01 | 2022-08-31 | bar: July 31 to August 31
Sprint analysis | bar: July 31 to August 4
Technical design | bar: August 5 to August 9
Development | bar: August 10 to August 22
Testing | bar: August 22 to August 31
Sprint 1 complete | bar: August 31
Exact dates for sprint 1 are yet to be determined
Exact dates for sprint 2 are yet to be determined
More months to be added as sprint 3 is approached
More sprints are to be added